## Sheet1
Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 |  | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. | Quote for CHINT | Quote No: 1010 | Sleater & Co. | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT |  | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT |  | Quote No: 1010 |  | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. |  | Quote for CHINT | Quote No: 1010 | Sleater & Co. | Quote for CHINT | Quote No: 1010
[11 empty] | 1. Document Details |  |  |  | 2. Project Details |  |  | 3. Overview of Project |  |  | 3. Overview of Project |  |  |  | 3. Overview of Project |  |  |  |  | 4. Proposed Hardware |  |  |  | 4. Proposed Hardware |  |  |  | 4. Proposed Hardware |  |  |  | 4. Proposed Hardware |  |  |  | 5. Project Details |  |  | 5. Project Details | [5 empty] | 5. Project Details |  |  |  | 5. Project Details |  |  |  | 5. Project Details |  |  |  |  | 6. Terms & Conditions |  |  | 7. Exceptions, Exclusions & Remarks |  |  |  | 8. Glossary
[14 empty] | The project proposal is in response to an enquiry received from BQ, BZ. The project will be located at CF. | [8 empty] | The scope of works section of this document outline Sleater & Co.'s | [5 empty] | 4.1 Bill of Materials |  |  |  | 4.2 PLC Hardware |  |  |  | 4.3 SCADA/HMI Software |  |  |  | 4.4 Control Panel Design |  |  |  | 5.1 Projects Schedule |  |  |  | 5.2 Project Cost Breakdown | [5 empty] | 5.3 Project Testing Philosophy |  |  |  | 5.5 Project Training Requirements/Cources |  |  |  | 5.6 Continuing Project Support |  |  |  | 6.1 Payment Terms |  |  | •The supplied project schedual assumes that each milestone is completed in a timely manner. Sleater & Co. will commit to achievining the stated phased in the stated duration. If any of the milestones are delayed due to outside influence, Sleater & Co. will not accept extra costs required to expedite any Sleater & Co. phase in order to meet subsequent milstones and prevent overall schedual impact. •Expedition of any phase, or recover lost time due to the unforseen, will require an approved change in order prior to execution •Out of scope items will be approached on a Change Order or Time and Materials (T&M) basis, agreed with the Company project management, prior to execution
[23 empty] | understanding of the work involved. It is based on Related |  |  |  |  | Supplier |  | Description | [9 empty] | Control Panel design and fabrications willl be carried out at our premises. We shall supply a full drawing Panel manual, general arrangement and shematic diagrams. All designs are subject to full issue control and revision. |  |  |  | Week |  | Activity |  | Description |  |  | Resources |  | Cost | Sleater & Co. will complete both FAT and SAT as per the following headings: •Hardware Installation Verification •Electrical Earthing/Bonding Verification •Electrical Sheilding Verification •Electrical Power Supply Verification •PLC Digital input Verification •PLC Digital Output Verification •PLC Analougue Input Verification •PLC Analougue Output Verfication •SCADA Alarms Verification •SCADA Message Verification •SCADA Screen Navigation | [7 empty] | •When the system has been accepted Sleater & Co. will provide telephone support by the project engineer responsible for the project for a period up to 2 months. The service will be offered free of charge. •If a site visit is required, the cost will be borne by the Company •After a period of 6 months, any telephone support will be charged at standard rates •Any modifications will be charged at standard rates |  |  |  | •The above price is quoted in Euro •All prices quoted are exclusive of VAT which will be charged at the appropriate rate unless your Company has an Authorised VAT Excemption •Errors & Ommissions Accepted •Goods remain in the ownership of Sleater & Co. until payment is received in full •This quotation is valid for 30 days •Payment is strictly due 30 days from the date of Invoice •Payment due: - 40% with order - 30% on sign-off of FDS - 20% on sign-off of FAT - 10% on sign-off of SAT | [7 empty] | Term | Meaning
[6 empty] | Table of Contents | [16 empty] | Documentation, two site visits and previous experience of maintaining | [50 empty] | FDS | Functional Design Specificatioins
[23 empty] | the Machine. | [50 empty] | OAT | Operational Acceptance Test
Electrical + Automation Contractors |  |  |  | 1 | Document Details |  |  | 3 |  | 1.1 | Document Location: | [62 empty] | FAT | Factory Acceptace Test
|  |  |  | 2 | Project Details |  |  | 4 | [5 empty] | The project proposal is based upon the details supplied in the Related Documents below. | [8 empty] | Any additional work not included in this section will require an approved | [50 empty] | SAT | Site Acceptance Test
|  |  |  | 2.1 | Related Documentation |  |  | 4 | [14 empty] | change order prior to the work being commenced. | [16 empty] | All our panels are built and tested to the highest standards including… | [33 empty] | IFC | Issue for Construction
|  |  |  | 3 | Overview of Project |  |  | 5 |  | 1.2 | Document Revision Number: | [62 empty] | PLC | Programmable Logic Controller
|  |  |  | 3.1 | Machine Functions & Layout |  |  | 7 | [5 empty] | 2.1 Related Documentation | [9 empty] | 3.1 Machine Functions and Layout | [15 empty] | •EN60439-1: Low Voltage switch-gear and control gear assemblies •ET101-2000 •EN60898: Circuit Breakers for over current protection •Directive 89/336/EEC Electromagnetic compatibility •EN60204: Safety of Machinery - Electrical Equipment of Machines •EN6047-1, Low Voltage Switch-gear and Control Gear Part 1 General Rules •EN60950: Safety of information technology equipment •EN60529: Degrees of protection provided bu enclosures •EN60742: Isolating transformers and safety isolating transformers •EN60999: Safety requirements for screw type and screw less type clamping units for electrical copper conductors | [33 empty] | SCADA | Supervisory, Control and Data Acquisition
|  |  |  | 4 | Proposed Hardware |  |  | 8 |  |  |  |  | Document Description |  |  | Owner | [6 empty] | Machine Functions |  | Quantity | Sleater & Co. Deliverables | [47 empty] | O&M | Operatrion and Maintenance
|  |  |  | 4.1 | PLC Hardware |  |  | 9 |  | 1.3 | Owner:
|  |  |  | 4.2 | SCADA/HMI Software |  |  | 10
|  |  |  | 4.3 | Control Panel Design |  |  | 11
|  |  |  | 5 | Project Details |  |  | 12 |  | 1.4 | Document Reference Number:
| Quotation for CHINT |  |  | 5.1 | Project Schedual |  |  | 12
| Quotation for 1010 |  |  | 5.2 | Project Cost Breakdown |  |  | 13
|  |  |  | 5.3 | Project Testing Philosophy |  |  | 14
|  |  |  | 5.4 | Project Documentation |  |  | 14
|  |  |  | 5.5 | Project Training Requirements/Courses |  |  | 15
|  |  |  | 5.6 | Continuing Project Support |  |  | 16 | [46 empty] | 5.4 Project Documentation
|  |  |  | 6 | Terms & Conditions |  |  | 17 | [45 empty] | Sleater & Co. will keep a Working Documentation copy for their records. They will not be updated because of customer modifications unless otherwise requested. There will be a standard charge for such updates, if this service is required.
|  |  |  | 6.1 | Payment Terms |  |  | 17
|  |  |  | 7 | Exceptions, Exclusions & Remarks |  |  | 18
|  |  |  | 8 | Glossary |  |  | 19
The document supplied to the customer shall incluse the following: •Master copy and backup copies of all source code •Functional Design Specification (FDS) with intergrated Bill of Materials (BOM) •Electrical Drawings •Vendor O & M Manuals •Calibration Certificates •Approved Site Acceptance Test document
[51 empty] | Total: |  | 0
|  | Page 1 of 19 |  |  |  | Page 2 of 19 |  |  |  |  | Page 3 of 19 |  |  |  | Page 4 of 19 |  |  | Page 5 of 19 |  |  | Page 6 of 19 |  |  |  | Page 7 of 19 |  |  |  |  | Page 8 of 19 |  |  |  | Page 9 of 19 |  |  |  | Page 10 of 19 |  |  |  | Page 11 of 19 |  |  |  | Page 12 of 19 |  |  |  | Page 13 of 19 | [5 empty] | Page 14 of 19 |  |  |  | Page 15 of 19 |  |  |  | Page 16 of 19 |  |  |  | Page 17 of 19 |  |  |  | Page 18 of 19 |  |  | Page 19 of 19
|  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 | [5 empty] | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  |  | ©Keith Sleater, Sleater & Co 2003 |  |  | ©Keith Sleater, Sleater & Co 2003